## Implementation Plan
DBT IMPLEMENTATION PLAN ¦ Start: 4 Mar 2026 ¦ 7.5 hrs/day ¦ Resources: A & B ¦ Dates updated from 6.5→7.5 hrs/day
Hour budgets fixed from original 6.5 hrs/day sizing. At 7.5 hrs/day, tasks complete sooner → earlier start & end dates cascade through plan.
# | Task | Res | Orig Days | New Days (@7.5h) | Hours Budget | Start Date | End Date | Category | Dependencies | Status | Notes | Risk
1 | DBT Project Setup & Config | A | 1 | 1 | 6.5h | 04-Mar-2026 | 04-Mar-2026 | Setup | — | Not Started | Repo init, profiles, dbt_project.yml | Low
2 | DBT Source Configuration | B | 1 | 1 | 6.5h | 05-Mar-2026 | 05-Mar-2026 | Setup | #1 | Not Started | sources.yml, freshness checks | Low
3 | Creation Staging Table and Data Load | A | 5 | 4 | 32.5h | 06-Mar-2026 | 11-Mar-2026 | Data | #2 | Not Started | Staging models + seed/load scripts | Medium
4 | Stage to Core Classification Model | B | 5 | 4 | 32.5h | 12-Mar-2026 | 17-Mar-2026 | Data | #3 | Not Started | Intermediate & core layer models | Medium
5 | Verify Existing Tags & Security Roles | B | 1 | 1 | 6.5h | 06-Mar-2026 | 06-Mar-2026 | Governance | #2 | Not Started | Audit existing Snowflake tags/roles | Medium
6 | Verify Existing Masking Policy & Macros | B | 1 | 1 | 6.5h | 09-Mar-2026 | 09-Mar-2026 | Governance | #5 | Not Started | Audit masking policies | Medium
7 | Provide Access: Landing DB → Governance DB | A&B | 1 | 1 | 6.5h | 09-Mar-2026 | 09-Mar-2026 | Governance | #5 | Not Started | Prerequisites: 3 tags on DB/schema, read access for SA role | Medium
8 | Create Macro – apply_classifications | A | 2.5 | 2 | 16.25h | 10-Mar-2026 | 11-Mar-2026 | Macros | #7 | Not Started |  | Low
9 | Create Macro – apply_tags | A | 2.5 | 2 | 16.25h | 12-Mar-2026 | 13-Mar-2026 | Macros | #8 | Not Started |  | Low
10 | Create Macro – apply_masking_policies | A | 2.5 | 2 | 16.25h | 16-Mar-2026 | 17-Mar-2026 | Macros | #9 | Not Started |  | Low
11 | PK/FK/BK Hashing Logic | B | 2.5 | 2 | 16.25h | 18-Mar-2026 | 19-Mar-2026 | Data | #4 | Not Started | Hash surrogate keys | Medium
12 | Macro Unit Tests | B | 5 | 4 | 32.5h | 20-Mar-2026 | 25-Mar-2026 | Testing | #10, #11 | Not Started | Unit test all 3 macros | Medium
13 | DBT Testing – Row Counts | A&B | 5 | 4 | 32.5h | 26-Mar-2026 | 31-Mar-2026 | Testing | #12 | Not Started | Generic + singular tests | Medium
14 | Setup New Zone Project for Masking Testing | A | 1 | 1 | 6.5h | 01-Apr-2026 | 01-Apr-2026 | Testing | #13 | Not Started |  | Medium
15 | Setup New Zone Database for Masking Testing | B | 1 | 1 | 6.5h | 02-Apr-2026 | 02-Apr-2026 | Testing | #14 | Not Started |  | Medium
16 | Working with Landing Ingestion Team (Test Schema) | A&B | 1 | 1 | 6.5h | 03-Apr-2026 | 03-Apr-2026 | Testing | #15 | Not Started | Coordinate new test schema | Medium
17 | End-to-End Validation | A&B | 2 | 1 | 13.0h | 06-Apr-2026 | 06-Apr-2026 | Testing | #16 | Not Started | Full pipeline E2E test | Medium
18 | DevOps – Repo & AD Groups | A | 1 | 1 | 6.5h | 05-Mar-2026 | 05-Mar-2026 | DevOps | #1 | Not Started | Branching strategy, AD group setup | Medium
19 | CI/CD Pipeline | A | 2 | 1 | 13.0h | 06-Mar-2026 | 06-Mar-2026 | DevOps | #18 | Not Started | GitHub Actions / Azure DevOps pipeline | Medium
20 | Airflow Workspace & DAGs | B | 2 | 1 | 13.0h | 07-Apr-2026 | 07-Apr-2026 | DevOps | #17 | Not Started | DAG authoring & connections | Medium
21 | RBAC – Implement | B | 1 | 1 | 6.5h | 10-Mar-2026 | 10-Mar-2026 | RBAC | #7 | Not Started | Role hierarchy in Snowflake | High
22 | RBAC – Validate | B | 1 | 1 | 6.5h | 11-Mar-2026 | 11-Mar-2026 | RBAC | #21 | Not Started | Privilege checks | High
23 | Transform DB RBAC – Implementation (own schema) | A&B | 1 | 1 | 6.5h | 12-Mar-2026 | 12-Mar-2026 | RBAC | #22 | Not Started |  | High
24 | Handover Checklist | A&B | 1 | 1 | 6.5h | 07-Apr-2026 | 07-Apr-2026 | Handover | #17, #23 | Not Started |  | Low
25 | Handover Meeting to DGM & Governance | A&B | 1 | 1 | 6.5h | 08-Apr-2026 | 08-Apr-2026 | Handover | #24 | Not Started | After first use case completed | Low
26 | Documentation | A | 2 | 1 | 13.0h | 07-Apr-2026 | 07-Apr-2026 | Docs | #17 | Not Started | Technical + runbook docs | Low
27 | Contingency / Risk Buffer | A&B | 2 | 1 | 13.0h | 09-Apr-2026 | 09-Apr-2026 | Buffer | #25, #26 | Not Started | Overflow & unplanned work | Low

## Work Day Plan
DBT PROJECT GANTT ¦ Start: 4 Mar 2026 ¦ 7.5 hrs/day ¦ Blue = Resource A Orange = Resource B Green = Shared A&B
|  |  | Week 1 |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6
# | Task | Res | 04 Wed | 05 Thu | 06 Fri | 09 Mon | 10 Tue | 11 Wed | 12 Thu | 13 Fri | 16 Mon | 17 Tue | 18 Wed | 19 Thu | 20 Fri | 23 Mon | 24 Tue | 25 Wed | 26 Thu | 27 Fri | 30 Mon | 31 Tue | 01 Wed | 02 Thu | 03 Fri | 06 Mon | 07 Tue | 08 Wed | 09 Thu | 10 Fri
1 | DBT Project Setup & Config | A
2 | DBT Source Configuration | B
3 | Creation Staging Table and Data Load | A
4 | Stage to Core Classification Model | B
5 | Verify Existing Tags & Security Roles | B
6 | Verify Existing Masking Policy & Macros | B
7 | Provide Access: Landing DB → Governance DB | A&B
8 | Create Macro – apply_classifications | A
9 | Create Macro – apply_tags | A
10 | Create Macro – apply_masking_policies | A
11 | PK/FK/BK Hashing Logic | B
12 | Macro Unit Tests | B
13 | DBT Testing – Row Counts | A&B
14 | Setup New Zone Project for Masking Testing | A
15 | Setup New Zone Database for Masking Testing | B
16 | Working with Landing Ingestion Team (Test Schema) | A&B
17 | End-to-End Validation | A&B
18 | DevOps – Repo & AD Groups | A
19 | CI/CD Pipeline | A
20 | Airflow Workspace & DAGs | B
21 | RBAC – Implement | B
22 | RBAC – Validate | B
23 | Transform DB RBAC – Implementation (own schema) | A&B
24 | Handover Checklist | A&B
25 | Handover Meeting to DGM & Governance | A&B
26 | Documentation | A
27 | Contingency / Risk Buffer | A&B

## Resource Allocation
RESOURCE ALLOCATION ¦ 6.5 hrs/day (original) → 7.5 hrs/day (actual) ¦ Dates & durations updated
Resource | Tasks | Orig Days (@6.5h) | New Days (@7.5h) | Days Saved | Hours Budget | Start Date | End Date | Categories
Resource A | 17 | 33.5 | 26 | -7.5d | 217.8h | 04-Mar-2026 | 09-Apr-2026 | Setup, Data, Governance, Macros, Testing, DevOps, RBAC, Handover, Docs, Buffer
Resource B | 18 | 34.5 | 28 | -6.5d | 224.2h | 05-Mar-2026 | 09-Apr-2026 | Setup, Data, Governance, Testing, DevOps, RBAC, Handover, Buffer
Both (A&B) | 8 | 14 | 11 | -3d | 91.0h | 09-Mar-2026 | 09-Apr-2026 | Governance, Testing, RBAC, Handover, Buffer
✅ Project completes 6.5 working day(s) earlier: 17-Apr-2026 → 09-Apr-2026
DURATION CHANGES
Tasks | Hour Budget | Orig Days | New Days | Saving
5-day tasks (3,4,12,13) | 32.5 hrs | 5 days | 4 days | -1 day
2.5-day tasks (8,9,10,11) | 16.25 hrs | 2.5 days | 2 days | -0.5 day
2-day tasks (17,19,20,26,27) | 13 hrs | 2 days | 1 day | -1 day
1-day tasks | 6.5 hrs | 1 day | 1 day | same
LEGEND
Resource A
Resource B
Shared A&B
RISK
Low
Medium
High