## Implementation Plan
DBT IMPLEMENTATION PLAN ¦ Start: 4 Mar 2026 ¦ 6.5 hrs/person/day ¦ Resources: A & B
Project: Snowflake DBT Data Governance & Classification Framework
# | Task | Resource | Duration (Days) | Hours (6.5/day) | Start Date | End Date | Category | Dependencies | Status | Notes | Risk
1 | DBT Project Setup & Config | A | 1 | 6.5 | 04-Mar-2026 | 04-Mar-2026 | Setup | — | Not Started | Repo init, profiles, dbt_project.yml | Low
2 | DBT Source Configuration | B | 1 | 6.5 | 05-Mar-2026 | 05-Mar-2026 | Setup | #1 | Not Started | sources.yml, freshness checks | Low
3 | Creation Staging Table and Data Load | A | 5 | 32.5 | 06-Mar-2026 | 12-Mar-2026 | Data | #2 | Not Started | 5 days × 6.5 hrs = 32.5 hrs ¦ Staging models + seed/load scripts | Medium
4 | Stage to Core Classification Model | B | 5 | 32.5 | 13-Mar-2026 | 19-Mar-2026 | Data | #3 | Not Started | 5 days × 6.5 hrs = 32.5 hrs ¦ Intermediate & core layer models | Medium
5 | Verify Existing Tags & Security Roles | B | 1 | 6.5 | 06-Mar-2026 | 06-Mar-2026 | Governance | #2 | Not Started | Audit existing Snowflake tags/roles | Medium
6 | Verify Existing Masking Policy & Macros | B | 1 | 6.5 | 09-Mar-2026 | 09-Mar-2026 | Governance | #5 | Not Started | Audit masking policies | Medium
7 | Provide Access: Landing DB → Governance DB | A&B | 1 | 6.5 | 09-Mar-2026 | 09-Mar-2026 | Governance | #5 | Not Started | Prerequisites: 3 tags on DB/schema, read access for SA role | Medium
8 | Create Macro – apply_classifications | A | 2.5 | 16.25 | 10-Mar-2026 | 12-Mar-2026 | Macros | #7 | Not Started | 2.5 days × 6.5 hrs = 16.25 hrs | Low
9 | Create Macro – apply_tags | A | 2.5 | 16.25 | 13-Mar-2026 | 17-Mar-2026 | Macros | #8 | Not Started | 2.5 days × 6.5 hrs = 16.25 hrs | Low
10 | Create Macro – apply_masking_policies | A | 2.5 | 16.25 | 18-Mar-2026 | 20-Mar-2026 | Macros | #9 | Not Started | 2.5 days × 6.5 hrs = 16.25 hrs | Low
11 | PK/FK/BK Hashing Logic | B | 2.5 | 16.25 | 20-Mar-2026 | 24-Mar-2026 | Data | #4 | Not Started | 2.5 days × 6.5 hrs = 16.25 hrs ¦ Hash surrogate keys | Medium
12 | Macro Unit Tests | B | 5 | 32.5 | 25-Mar-2026 | 31-Mar-2026 | Testing | #10, #11 | Not Started | 5 days × 6.5 hrs = 32.5 hrs ¦ Unit test all 3 macros | Medium
13 | DBT Testing – Row Counts | A&B | 5 | 32.5 | 01-Apr-2026 | 07-Apr-2026 | Testing | #12 | Not Started | 5 days × 6.5 hrs = 32.5 hrs ¦ Generic + singular tests | Medium
14 | Setup New Zone Project for Masking Testing | A | 1 | 6.5 | 08-Apr-2026 | 08-Apr-2026 | Testing | #13 | Not Started |  | Medium
15 | Setup New Zone Database for Masking Testing | B | 1 | 6.5 | 09-Apr-2026 | 09-Apr-2026 | Testing | #14 | Not Started |  | Medium
16 | Working with Landing Ingestion Team (Test Schema) | A&B | 1 | 6.5 | 10-Apr-2026 | 10-Apr-2026 | Testing | #15 | Not Started | Coordinate new test schema | Medium
17 | End-to-End Validation | A&B | 2 | 13 | 13-Apr-2026 | 14-Apr-2026 | Testing | #16 | Not Started | Full pipeline E2E test | Medium
18 | DevOps – Repo & AD Groups | A | 1 | 6.5 | 05-Mar-2026 | 05-Mar-2026 | DevOps | #1 | Not Started | Branching strategy, AD group setup | Medium
19 | CI/CD Pipeline | A | 2 | 13 | 06-Mar-2026 | 09-Mar-2026 | DevOps | #18 | Not Started | GitHub Actions / Azure DevOps pipeline | Medium
20 | Airflow Workspace & DAGs | B | 2 | 13 | 15-Apr-2026 | 16-Apr-2026 | DevOps | #17 | Not Started | DAG authoring & connections | Medium
21 | RBAC – Implement | B | 1 | 6.5 | 10-Mar-2026 | 10-Mar-2026 | RBAC | #7 | Not Started | Role hierarchy in Snowflake | High
22 | RBAC – Validate | B | 1 | 6.5 | 11-Mar-2026 | 11-Mar-2026 | RBAC | #21 | Not Started | Privilege checks | High
23 | Transform DB RBAC – Implementation (own schema) | A&B | 1 | 6.5 | 12-Mar-2026 | 12-Mar-2026 | RBAC | #22 | Not Started |  | High
24 | Handover Checklist | A&B | 1 | 6.5 | 15-Apr-2026 | 15-Apr-2026 | Handover | #17, #23 | Not Started |  | Low
25 | Handover Meeting to DGM & Governance | A&B | 1 | 6.5 | 16-Apr-2026 | 16-Apr-2026 | Handover | #24 | Not Started | After first use case completed | Low
26 | Documentation | A | 2 | 13 | 15-Apr-2026 | 16-Apr-2026 | Docs | #17 | Not Started | Technical + runbook docs | Low
27 | Contingency / Risk Buffer | A&B | 2 | 13 | 17-Apr-2026 | 20-Apr-2026 | Buffer | #25, #26 | Not Started | Overflow & unplanned work | Low

## Work Day Plan
DBT PROJECT – WORK DAY GANTT ¦ 4 Mar 2026 onwards ¦ 6.5 hrs/day ¦ Resource A (Blue) Resource B (Orange) Shared (Green)
|  |  | Week 1 |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8
# | Task | Res | 04 Wed | 05 Thu | 06 Fri | 09 Mon | 10 Tue | 11 Wed | 12 Thu | 13 Fri | 16 Mon | 17 Tue | 18 Wed | 19 Thu | 20 Fri | 23 Mon | 24 Tue | 25 Wed | 26 Thu | 27 Fri | 30 Mon | 31 Tue | 01 Wed | 02 Thu | 03 Fri | 06 Mon | 07 Tue | 08 Wed | 09 Thu | 10 Fri | 13 Mon | 14 Tue | 15 Wed | 16 Thu | 17 Fri | 20 Mon | 21 Tue
1 | DBT Project Setup & Config | A
2 | DBT Source Configuration | B
3 | Creation Staging Table and Data Load | A
4 | Stage to Core Classification Model | B
5 | Verify Existing Tags & Security Roles | B
6 | Verify Existing Masking Policy & Macros | B
7 | Provide Access: Landing DB → Governance DB | A&B
8 | Create Macro – apply_classifications | A
9 | Create Macro – apply_tags | A
10 | Create Macro – apply_masking_policies | A
11 | PK/FK/BK Hashing Logic | B
12 | Macro Unit Tests | B
13 | DBT Testing – Row Counts | A&B
14 | Setup New Zone Project for Masking Testing | A
15 | Setup New Zone Database for Masking Testing | B
16 | Working with Landing Ingestion Team (Test Schema) | A&B
17 | End-to-End Validation | A&B
18 | DevOps – Repo & AD Groups | A
19 | CI/CD Pipeline | A
20 | Airflow Workspace & DAGs | B
21 | RBAC – Implement | B
22 | RBAC – Validate | B
23 | Transform DB RBAC – Implementation (own schema) | A&B
24 | Handover Checklist | A&B
25 | Handover Meeting to DGM & Governance | A&B
26 | Documentation | A
27 | Contingency / Risk Buffer | A&B

## Resource Allocation
RESOURCE ALLOCATION SUMMARY
Resource | Total Tasks | Total Days | Total Hours (@ 6.5/day) | Start Date | End Date | Categories Covered | Notes
Resource A | 17 | 33.5 | 217.8 hrs | 04-Mar-2026 | 20-Apr-2026 | Setup, Data, Governance, Macros, Testing, DevOps, RBAC, Handover, Docs, Buffer | Parallel tracks where possible; A&B tasks require coordination
Resource B | 18 | 34.5 | 224.2 hrs | 05-Mar-2026 | 20-Apr-2026 | Setup, Data, Governance, Testing, DevOps, RBAC, Handover, Buffer | Parallel tracks where possible; A&B tasks require coordination
Both (A&B) | 8 | 14 | 91.0 hrs | 09-Mar-2026 | 20-Apr-2026 | Governance, Testing, RBAC, Handover, Buffer | Parallel tracks where possible; A&B tasks require coordination
LEGEND
Resource A tasks
Resource B tasks
Shared A&B tasks
DURATION NOTES
Tasks 3 & 4: | 5 days each = 32.5 hrs per task
Tasks 8,9,10,11: | 2.5 days each = 16.25 hrs per task
Tasks 12 & 13: | 5 days each = 32.5 hrs per task
All others: | 1–2 days = 6.5–13 hrs per task
RISK LEVELS
Low
Medium
High